## Offer Rules
Situation | Price | Example
Order via link in bio (website) | Normal price - no discount | 1 cheesecake box = 7 KD
WhatsApp order, 1 box | Normal price | 7 KD
WhatsApp order, 2+ boxes | 20% off the WHOLE order | 2 boxes 14 KD -> 11.200 KD ¦ 3 boxes 21 KD -> 16.800 KD
Zwaratna Alyoum alone (any channel) | 19 KD flat - no 20% | 19 KD
Zwaratna Alyoum + 1 more box, on WhatsApp | 20% off the WHOLE order (matches 'على الفاتورة كاملة' printed on the offer posts) | 19 + 7 = 26 KD -> 20.800 KD
Zwaratna contents (default) | Sambosa, Cheese Roll, Mini Cheesecake, Mini Croissant | Customer may swap any box; swapping in Sugar Clouds makes it 20 KD
Naming | تشيز رول = أصابع جبن (same product). Captions use تشيز رول
Campaign window | Thu 8 Oct - Sat 31 Oct 2026 | Recommended: a hard end date creates urgency; 'October' alone does not
WhatsApp | 92217054 | wa.me/96592217054

## Schedule
Phase | Date | Time (KW) | Channel | Format | Creative (Drive file #) | Caption / sticker | Notes
W1 Launch | Thu 8 Oct | 7:00 PM | WhatsApp | Broadcast + Status | 02 Offer AR story + 04 Menu | CAP-WA-BROADCAST | Send to every past customer. Status = same 2 images
W1 Launch | Thu 8 Oct | 8:00 PM | Instagram | Feed post (PIN to top) | 03 Offer AR feed-4x5 | CAP-FEED-OFFER | Pin it. Only feed-size file we have
W1 Launch | Thu 8 Oct | 8:05 PM | Instagram | Stories x3 | 02 Offer AR -> 04 Menu -> 01 Offer EN | Sticker: link wa.me/96592217054 'اطلب واتساب' | Save as Highlight 'العرض'
W1 Launch | Thu 8 Oct | 9:00 PM | TikTok | Video | 16 Video 1 | CAP-VIDEO-1 | TikTok first - Thu night is peak
W1 Launch | Fri 9 Oct | 1:00 PM | Instagram | Reel (share to feed) | 16 Video 1 | CAP-VIDEO-1
W1 Launch | Fri 9 Oct | 8:00 PM | Instagram | Stories x2 | 05 Bundle -> 02 Offer AR | Sticker: link + 'تقدر تبدّل البوكسات' | Weekend = zwara night
W1 Launch | Sat 10 Oct | 8:00 PM | Instagram | Stories x3 | 06 Clouds box -> 07 Clouds hand -> 02 Offer AR | Poll sticker: 'كاكاو ولا بستاشيو؟' | Best seller first
W1 Launch | Sat 10 Oct | 9:00 PM | TikTok | Photo carousel | 04 Menu, 05 Bundle, 06, 08, 11, 12, 15 | CAP-TT-MENU
W1 Launch | Sun 11 Oct | 8:00 PM | Instagram | Stories x3 | 08 Cheese roll dip -> 09 Duo -> 02 Offer AR | Text: 'بوكسين = خصم 20%'
W1 Launch | Mon 12 Oct | 8:00 PM | Instagram + WA Status | Stories x3 | 12 Croissant box -> 13 Croissant dip -> 02
W1 Launch | Tue 13 Oct | 8:00 PM | Instagram + WA Status | Stories x3 | 14 Sambosa dip -> 15 Sambosa box -> 02 | Push the weak seller
W1 Launch | Wed 14 Oct | 8:00 PM | Instagram + WA Status | Stories x3 | 11 Cheesecake box -> 10 Cheesecake close-up -> 04 Menu | Quiz sticker: 'جم حبة في البوكس؟'
W2 Rotation | Thu 15 Oct | 9:00 PM | TikTok | Video | 17 Video 2 | CAP-VIDEO-2
W2 Rotation | Fri 16 Oct | 1:00 PM | Instagram | Reel (share to feed) | 17 Video 2 | CAP-VIDEO-2
W2 Rotation | Fri 16 Oct | 8:00 PM | Instagram + WA Status | Stories x2 | 05 Bundle -> 02 Offer AR
W2 Rotation | Sat 17 Oct | 8:00 PM | Instagram + WA Status | Stories x3 | 07 Clouds hand -> 06 Clouds box -> 02
W2 Rotation | Sun 18 Oct | 8:00 PM | Instagram | Stories | Repost customer orders / DMs (screenshot with permission) |  | Social proof - ask every WhatsApp customer for a photo
W2 Rotation | Mon 19 Oct | 9:00 PM | TikTok | Photo carousel | 09 Duo, 08, 11, 13, 14, 02 | CAP-TT-OFFER
W2 Rotation | Mon-Wed 19-21 Oct | 8:00 PM | Instagram + WA Status | Stories x3 daily | Rotate product pairs as in W1 (Croissant / Sambosa / Cheesecake)
W3 Mid-push | Thu 22 Oct | 7:00 PM | WhatsApp | Broadcast #2 | 05 Bundle + 02 Offer | CAP-WA-BROADCAST-2 | Weekend reminder
W3 Mid-push | Thu 22 Oct | 9:00 PM | TikTok | Video (repost) | 16 Video 1 - new caption + different sound | CAP-VIDEO-1 (alt hook) | TikTok rewards reposts with a new hook
W3 Mid-push | Fri 23 Oct | 1:00 PM | Instagram | Reel | Best performer of Video 1 / 2 - trimmed 15s cut | CAP-VIDEO-2
W3 Mid-push | Fri-Sat 23-24 Oct | 8:00 PM | Instagram + WA Status | Stories x3 daily | 05 Bundle / 06-07 Clouds / customer reposts
W4 Countdown | Sun 25 Oct | 8:00 PM | Instagram + TikTok + WA | Story / photo | NEW: 'باقي أسبوع' countdown story (designer) | CAP-COUNTDOWN | NEEDS DESIGN
W4 Countdown | Thu 29 Oct | 7:00 PM | WhatsApp | Broadcast #3 | 02 Offer + countdown | CAP-WA-LASTCALL
W4 Countdown | Thu 29 Oct | 8:00 PM | Instagram | Stories x3 + countdown sticker | 02 -> 04 -> 05 | IG countdown sticker set to 31 Oct 11:59 PM
W4 Countdown | Sat 31 Oct | 12:00 PM | Instagram + TikTok + WA | Story / photo | NEW: 'آخر يوم' story (designer) | CAP-COUNTDOWN (last day) | NEEDS DESIGN

## Captions
Caption ID | Use for | Caption (Arabic)
CAP-FEED-OFFER | IG feed - 03 Offer | عرض حصري على الواتساب 💙 خصم 20% على الفاتورة كاملة لما تطلب بوكسين أو أكثر 🎁 اختار اللي يعجبك: 🥟 سمبوسة المكسرات — 7 د.ك 🧀 تشيز رول (أصابع جبن) — 7 د.ك 🍰 ميني تشيز كيك — 7 د.ك 🥐 ميني كرواسون — 7 د.ك ☁️ شوقر كلاودز — 8 د.ك مثال: بوكسين بـ 14 د.ك ← تدفع 11.200 بس 👌 📲 اطلب واتساب: 92217054 العرض لين 31 أكتوبر — على طلبات الواتساب فقط #شوقر #حلويات_الكويت #ضيافة #زوارة #الكويت #عروض_الكويت
CAP-BUNDLE | Bundle - 05 (feed / TikTok / WA) | زوارتنا اليوم 🤍 4 بوكسات بكيس واحد بـ 19 د.ك بس: 🥟 سمبوسة المكسرات 🧀 تشيز رول 🍰 ميني تشيز كيك 🥐 ميني كرواسون تبي تغيّر بوكس؟ قول لنا ونبدّله حسب ذوقك 😉 💡 وإذا أضفت أي بوكس فوقها بالواتساب، تاخذ خصم 20% على الطلب كامل. 📲 92217054 ¦ أو الرابط في البايو #زوارتنا_اليوم #شوقر #ضيافة #حلويات_الكويت
CAP-VIDEO-1 | Reel/TikTok - Video 1 (unboxing) | فتحنا البوكسات وحدة وحدة… أي وحدة بتبدأ فيها؟ 👀👇 كل بوكس 7 د.ك (الكلاودز 8) 🎁 بوكسين أو أكثر من الواتساب = خصم 20% على الفاتورة كاملة 📲 92217054 #شوقر #حلويات_الكويت #ضيافة #زوارة #unboxing #الكويت
CAP-VIDEO-1 (alt hook) | TikTok repost - Video 1 | لو جتك زوارة الليلة… هذا الحل 🤍 بوكسين أو أكثر من الواتساب = خصم 20% 📲 92217054 #حلويات_الكويت #زوارة #شوقر #fyp
CAP-VIDEO-2 | Reel/TikTok - Video 2 (unboxing) | ضيافة كاملة بدون تعب 🤍✨ سمبوسة، تشيز رول، ميني تشيز كيك، كرواسون وكلاودز… كلها تجيك لين الباب. اطلب بوكسين أو أكثر من الواتساب وخذ خصم 20% 🎁 📲 92217054 العرض لين 31 أكتوبر #شوقر #ضيافة #حلويات_الكويت #زوارة #الكويت
CAP-TT-MENU | TikTok photo carousel - menu | منيو شوقر كامل 📋 أي بوكس تختار؟ 👇 بوكسين أو أكثر من الواتساب = خصم 20% 💙 📲 92217054 #حلويات_الكويت #ضيافة #زوارة #الكويت #fyp
CAP-TT-OFFER | TikTok photo carousel - offer | تبي توفّر؟ اطلب بوكسين من الواتساب وخذ 20% على الفاتورة كاملة 🎁 📲 92217054 #شوقر #عروض_الكويت #حلويات_الكويت #fyp
CAP-PRODUCT-LINE | Add to ANY product post caption | أو اطلب بالواتساب ووفّر 20% على بوكسين وأكثر 📲 92217054
CAP-WA-BROADCAST | WhatsApp broadcast #1 (launch) | هلا 🤍 معاك The Sugar عرض حصري لعملاء الواتساب: خصم 20% على الفاتورة كاملة لما تطلب بوكسين أو أكثر 🎁 المنيو بالصورة 👆 ردّ على هالرسالة باللي تبيه ونرتب لك الطلب 👌 العرض لين 31 أكتوبر
CAP-WA-BROADCAST-2 | WhatsApp broadcast #2 (weekend) | زوارة الويكند علينا 🤍 زوارتنا اليوم بـ 19 د.ك — وإذا أضفت بوكس فوقها تاخذ خصم 20% على الطلب كامل 🎁 ردّ بـ "زوارة" ونرتب لك 👌
CAP-WA-LASTCALL | WhatsApp broadcast #3 (last call) | آخر أيام عرض الواتساب ⏳ خصم 20% على بوكسين أو أكثر — ينتهي السبت 31 أكتوبر ردّ على هالرسالة واطلب قبل لا يخلص 💙
CAP-COUNTDOWN | Countdown story / TikTok text | باقي أسبوع على نهاية العرض ⏳ / آخر يوم! ⏰ خصم 20% على بوكسين أو أكثر — واتساب فقط 📲 92217054

## Creative Map
# | Drive file | What it is | Size | Use on
01 | 01_Offer-20off-WhatsApp_EN_story | 20% offer, English | 9:16 | IG story (English audience)
02 | 02_Offer-20off-WhatsApp_AR_story | 20% offer, Arabic | 9:16 | Closing frame of every story sequence; WA status
03 | 03_Offer-20off-WhatsApp_AR_feed-4x5 | 20% offer, Arabic | 4:5 | IG feed (pinned)
04 | 04_Menu-AllBoxes-Prices_AR_story | Full menu with prices | 9:16 | IG story highlight, WA broadcast, TikTok
05 | 05_Bundle-ZwaratnaAlyoum-19KD_AR_story | Zwaratna bundle 19 KD (photo shows Clouds, not Croissant) | 9:16 | Weekend stories, TikTok
06-07 | SugarClouds box / hand | Best seller, 8 KD | 9:16 | Stories, TikTok
08 | CheeseRolls dip | Cheese roll 7 KD | 9:16 | Stories, TikTok
09 | Duo CheeseRolls + Cheesecake | 'Hosting duo' - perfect for 2-box offer | 9:16 | Stories, TikTok
10-11 | MiniCheesecake close-up / box | 7 KD | 9:16 | Stories, TikTok
12-13 | MiniCroissant box / dip | 7 KD | 9:16 | Stories, TikTok
14-15 | NutSambosa dip / box | 7 KD | 9:16 | Stories, TikTok
16 | Video 1 | Unboxing, woman, captions per product | video | Reel + TikTok
17 | Video 2 | Unboxing, different style/music | video | Reel + TikTok